Dolly-15k FL × PEFT Research Placement

Week 2 Progress Report

Author: hufs0529

Date: 2026-08-21

Repository: github.com/hufs0529/peft_fl_STEM_placement (branch: week2)

# 1. Research Question

Does the benefit of FL drift correction persist even as PEFT compression intensifies?

Following advisor feedback after Week 1, the focus of this question is being adjusted toward the correlation between compression rate and data non-IID intensity — see Section 4.

# 2. Work Completed in Week 2

Per advisor feedback on the Week 1 report (the FL Parameter Helper section was not directly relevant to the research objective), this report focuses on content tied directly to the research design rather than pure implementation detail.

## 2.1 Dolly-15k Data Pipeline

Loaded the full 15,011-example dataset and carved out a held-out evaluation set (10%, drawn evenly per category) shared by all clients. This split is fixed before client partitioning, so the evaluation basis stays identical across experimental conditions.

## 2.2 Dirichlet Non-IID Partitioning — the Central Variable of This Study

Implemented Dirichlet(alpha)-based non-IID partitioning across 8 clients, keyed on the dataset's category field. A smaller alpha (e.g. 0.1) produces strongly skewed (non-IID) client distributions; a larger alpha (e.g. 1.0) approaches an even (IID) split.

Resampling safeguard: Categories with fewer samples than a threshold are upsampled so every client can secure a minimum number of training examples per category.

Verification: Implemented and tested a utility that quantifies how non-IID a partition actually is, to confirm smaller alpha values genuinely produce stronger non-IID splits.

This alpha parameter is the central axis of the redesigned experiment proposed in Section 4.

# 3. Original Research Plan (Recap)

The original proposal called for the following design:

(1) Data distribution: Dirichlet alpha fixed at 0.5 (no sweep).

(2) Core experiment: Run all 6 combinations of 3 FL algorithms (FedAvg/FedProx/SCAFFOLD) x 2 PEFT methods (LoRA/QLoRA) to test whether the benefit of correction sophistication persists as quantization intensifies.

(3) Diagnostic experiments: Select the best-performing combination among the 6, then run DoRA (an unquantized control) and a local_epochs=5 robustness check.

# 4. Advisor Feedback and Proposed Experimental Redesign

Advisor Feedback

"This project's focus should be the correlation between compression rate and non-IID intensity." Rather than holding alpha at a single fixed value, the suggestion is to vary compression rate and alpha together and directly compare the correlation between the two axes.

Reflecting this feedback, we propose the following 3 (compression) x 2 (FL) x 3 (alpha) = 18-combination design (pending advisor confirmation):

| Compression | FL | alpha=0.1 | alpha=0.5 | alpha=1.0 |
| --- | --- | --- | --- | --- |
| LoRA (uncompressed) | FedAvg | ✓ | ✓ | ✓ |
| LoRA (uncompressed) | FedProx | ✓ | ✓ | ✓ |
| QLoRA 8-bit | FedAvg | ✓ | ✓ | ✓ |
| QLoRA 8-bit | FedProx | ✓ | ✓ | ✓ |
| QLoRA 4-bit | FedAvg | ✓ | ✓ | ✓ |
| QLoRA 4-bit | FedProx | ✓ | ✓ | ✓ |

## 4.1 Rationale for This Design

Directly tests the compression x non-IID correlation: Comparing all 3 compression levels (uncompressed/8-bit/4-bit) at the same 3 alpha points (0.1/0.5/1.0) lets us directly observe, as a grid, how much worse compression makes performance under non-IID conditions.

Keeps the run count manageable: Narrowing from 3 FL algorithms to 2 (FedAvg/FedProx, dropping SCAFFOLD) keeps the total run count manageable (18) — SCAFFOLD's code and tests remain in the codebase but are excluded from this core design.

Produces a quantitative answer: We plan to quantify, via a Pearson correlation coefficient, how much the compression penalty (4-bit performance minus uncompressed performance) grows as alpha decreases (0.1, strong non-IID) versus increases (1.0, near-IID).

## 4.2 Changes from the Original Plan

| Item | Original Plan | Proposed Revision |
| --- | --- | --- |
| Dirichlet alpha | Fixed at 0.5 | Swept: 0.1 / 0.5 / 1.0 |
| Compression conditions | 2 levels: LoRA / QLoRA (4-bit) | 3 levels: uncompressed / 8-bit / 4-bit |
| FL algorithms | 3: FedAvg / FedProx / SCAFFOLD | 2: FedAvg / FedProx |
| Total core runs | 6 | 18 |
| Key deliverable | FL correction x quantization interaction | Compression rate x non-IID correlation |

Because the total run count grows from 6 to 18, GPU budget and time will be re-estimated separately once additional conditions (e.g. model size) are confirmed.

# 5. Empirical Verification: Does Partitioning Behave as Intended?

Before committing to the 18-combination design, we verified — on the real, full Dolly-15k dataset (15,011 examples, 8 native categories) with the actual experimental client count (8 clients) — that Dirichlet(alpha) partitioning genuinely produces the intended range of non-IID intensity at all three proposed alpha values.

## 5.1 Heterogeneity Score by alpha

heterogeneity_score quantifies how skewed a partition is (0 = perfectly even, 1 = perfectly skewed), approximated as the average, across clients, of each client's dominant-category share.

| alpha | heterogeneity_score | Clients holding all 8 categories |
| --- | --- | --- |
| 0.1 (strong non-IID) | 0.607 | 1 of 8 |
| 0.5 (moderate) | 0.501 | 7 of 8 |
| 1.0 (near-IID) | 0.351 | 8 of 8 |

The score decreases monotonically as alpha grows from 0.1 to 1.0, confirming the partitioning function behaves as intended at the actual 8-client scale used in the proposed experiment.

## 5.2 What This Looks Like at the Client Level

alpha=0.1: One client held only 3 of 8 categories, dominated by a single category (e.g. 563 of ~565 examples in one category); another held all 8 but with one category alone contributing over 3,100 examples — a clear client-specialization pattern.

alpha=0.5: 7 of 8 clients already hold all 8 categories, but per-category counts remain visibly uneven within a client (e.g. one category at ~1,067 vs. another at single digits).

alpha=1.0: All 8 clients hold all 8 categories with comparatively balanced counts across categories.

This confirms that alpha=0.1 is where genuinely extreme non-IID conditions (some clients nearly blind to most task categories) actually emerge — directly motivating why the 3-point sweep, rather than a single fixed alpha, is needed to observe the compression x non-IID correlation the advisor asked about.

# 6. Next Steps

To be confirmed: Advisor confirmation/approval of the 18-combination design above.

Planned for Week 3: Implement FedProx/SCAFFOLD integration, checkpointing, and convergence criteria (SCAFFOLD code retained, excluded only from the core run set).

Planned for Week 4: Prepare the execution script for the 18-combination main experiment, pending approved design.